## Start Here
SEO Plan Template: The First 90 Days
A working template for an SEO plan: a dated baseline, decisions scored on impact and effort, a 12-week Gantt by team with dependencies and blockers, and a read date for every change. Companion to drewgarrett.org/blog/seo-strategy/seo-plan.
How to use it
1 · Set the start date | Enter the Monday your plan starts in the Plan start date cell below. Every date in the workbook follows it.
2 · Record the baseline | On Baseline, log where the site stands before anything changes, with the date and the source.
3 · Score the decisions | On Decisions, list every possible move and score impact and effort from 1 to 5. The quadrant and priority order fill in automatically.
4 · Plan the 90 days | On 90-Day Gantt, give each task a team, a start week, a length, and the task it depends on. Bars and blocker flags update on their own.
5 · Read on schedule | On Read Dates, record each result on its date and decide to keep or drop the change. At week 12, re-baseline and plan the next quarter.
Plan settings
Setting | Value | How it is used
Plan start date | 2026-10-05 | Week 1 starts on this date. Change it and every week header and read date moves with it.
High impact at or above | 3 | Impact scores (1 to 5) at or above this count as high impact.
Low effort at or below | 2 | Effort scores (1 to 5) at or below this count as low effort.
Impact and effort quadrants
Quadrant | Order | What to do with it
Do first | 1 | High impact, low effort. Ship in the first weeks; quick wins build momentum.
Plan and schedule | 2 | High impact, high effort. The core of the quarter: pilot first, then scale.
Batch | 3 | Low impact, low effort. Fill gaps between bigger work.
Cut | 4 | Low impact, high effort. Drop it from the plan and write down why.
Team key (used on the Gantt)
Team | Letter on bars | Owns
SEO | S | Audit, keyword map, AI prompt set, specs, the plan itself
Content | C | Rewrites, briefs, retrofits, consolidation
Dev | D | Indexation fixes, templates, redirects, anything in the codebase
Design | G | Page templates and layouts
Analytics | A | Baseline pulls, tracking, read dates
Leadership | L | Goal, approvals, budget and sprint slots
Legend
Editable cell | Fill these in
White cell | Formula; leave it
Rows marked Example hold fictional values so you can see the formulas work. Overwrite them.
Note on B13: Example date. Replace it with your plan's first Monday.

## Baseline
Baseline
Where the site stands before anything changes. Date every row. A result you cannot compare to a dated baseline cannot be attributed to the plan.
Metric | Page group | Value | Date recorded | Source | Notes | Row type
Indexed pages | All | 1240 |  | Search Console, Pages report |  | Example
Pages in crawled, currently not indexed | All | 310 |  | Search Console, Pages report |  | Example
Top-10 keywords | Comparison pages | 85 |  | Rank tracker export |  | Example
Top-3 keywords | Comparison pages | 22 |  | Rank tracker export |  | Example
Organic-influenced demos (quarter) | All | 40 |  | CRM, multi-touch report |  | Example
AI-answer presence (named, 30 prompts) | Category prompts | 30% |  | Manual prompt set, 4 AI products | Share of prompts where the brand is named in the answer | Example
In flight: section migration | Integrations | Mid-migration |  | Previous owner's redirect map | Leave alone until it settles; read it separately | Example

## Decisions
Decisions: impact and effort
List every possible move and score it 1 to 5 on impact (how much it could move the goal) and effort (how much work it takes to ship). The quadrant and order fill in from the thresholds on Start Here.
ID | Decision | Page group | Lead team | Impact (1-5) | Effort (1-5) | Quadrant | Priority order | Metric it moves | Baseline | Target | Read week | Read date | Status
D1 | Fix canonicals and sitemap so integration pages get indexed | Integrations | Dev | 5 | 2 |  |  | Indexed integration pages | 40 | 110 | 4 |  | Proposed
D2 | Rewrite H1s and intros on striking-distance comparison pages | Comparison pages | Content | 4 | 2 |  |  | Top-3 keywords | 22 | 35 | 8 |  | Proposed
D3 | Rebuild the product-page template (pilot on 8 pages first) | Product pages | Dev | 5 | 4 |  |  | Organic-influenced demos | 40 | 50 | 12 |  | Proposed
D4 | Answer-first retrofit of pages AI already reads | Category guides | Content | 4 | 3 |  |  | AI-answer presence | 30% | 40% | 8 |  | Proposed
D5 | Add alt text to older blog images | Blog | Content | 2 | 1 |  |  | Image search clicks | 150 | 180 | 12 |  | Proposed
D6 | Rewrite 120 archive pages nobody searches for | Archive | Content | 1 | 5 |  |  | None worth tracking |  |  |  |  | Drop
Rows D1 to D6 are fictional examples. D6 shows a low impact, high effort move: it lands in Cut and stays out of the plan.
Note on H4: Lower number = do sooner. Quadrant first (x10), then higher impact and lower effort break ties. Sort ascending by this column.

## 90-Day Gantt
90-Day Gantt: who does what, when, and what it waits on
One row per task. Give it a team, a start week, a length in weeks, and the task it depends on. Bars fill in by team (with the team letter), and Blocker status flags any task whose dependency is not Done yet.
Teams: | S · SEO | C · Content | D · Dev | G · Design | A · Analytics | L · Leadership
Week of
ID | Task | Team | Priority | Depends on | Blocker status | Blocker note | Start wk | Weeks | End wk | Status | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12
Week number → | [10 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Weeks 1 to 3 · Baseline and diagnose
T01 | Kick off: confirm the goal, access, and stakeholders | Leadership | Setup |  |  |  | 1 | 1 |  | Done
T02 | Pull the baseline: Search Console, GA4, CRM | Analytics | Setup | T01 |  | Needs admin access to GA4 and the CRM | 1 | 2 |  | In progress
T03 | Crawl and technical audit | SEO | Setup | T01 |  |  | 1 | 2 |  | In progress
T04 | Inventory in-flight work: migrations, redirects, crawl rules, drafts | SEO | Setup | T01 |  | Needs the previous owner's notes | 1 | 1 |  | Done
T05 | Build the AI prompt set and record the AI-answer baseline | SEO | Setup | T01 |  |  | 2 | 1 |  | Not started
T06 | Content inventory and keyword map | Content | Setup | T02 |  |  | 2 | 2 |  | Not started
T07 | Score decisions on impact and effort; approve the plan | Leadership | Setup | T06 |  | Needs every baseline task Done | 3 | 1 |  | Not started
Weeks 4 to 8 · Fix and pilot
T08 | Fix indexation blockers: canonicals, noindex, sitemap | Dev | Do first | T07 |  | Needs a slot in the dev sprint | 4 | 2 |  | Not started
T09 | Rewrite H1s and intros on striking-distance pages | Content | Do first | T07 |  |  | 4 | 3 |  | Not started
T10 | Design the pilot page template | Design | Plan and schedule | T07 |  |  | 4 | 1 |  | Not started
T11 | Build the pilot template on 8 pages | Dev | Plan and schedule | T10 |  | Waits on design sign-off | 5 | 2 |  | Not started
T12 | Answer-first retrofit of the pilot pages (AI search) | Content | Plan and schedule | T05 |  |  | 5 | 2 |  | Not started
T13 | Read: indexation and technical fixes | Analytics | Read | T08 |  |  | 6 | 1 |  | Not started
T14 | Read: pilot results (rankings, AI-answer presence) | Analytics | Read | T11 |  |  | 8 | 1 |  | Not started
Weeks 9 to 12 · Scale and set the next quarter
T15 | Roll out the proven template sitewide | Dev | Plan and schedule | T14 |  | Only if the pilot read is positive | 9 | 3 |  | Not started
T16 | Consolidate overlapping blog posts | Content | Plan and schedule | T14 |  |  | 9 | 2 |  | Not started
T17 | Ship redirects for the consolidated posts | Dev | Plan and schedule | T16 |  | Needs the final redirect map | 11 | 1 |  | Not started
T18 | Re-run the AI prompt set and compare to baseline | SEO | Read | T12 |  |  | 12 | 1 |  | Not started
T19 | Re-baseline every metric | Analytics | Read | T15 |  |  | 12 | 1 |  | Not started
T20 | Write the next quarter's plan | SEO | Setup | T19 |  | Needs the re-baseline | 12 | 1 |  | Not started
Tasks T01 to T20 are a fictional example plan. Keep the structure, replace the tasks. Add rows inside the table so the formulas apply.

## Read Dates
Read dates: what each decision did
Pulled from Decisions. On each read date, record the result and decide whether to keep the change, drop it, or extend the read.
ID | Decision | Metric | Baseline | Target | Read date | Result (enter on the date) | Keep, drop, or extend | Notes